## Sheet1
BUG ID | Title | Severity | Status | Step to Reproduce | Dev.Stutus
UI001 | Login page lack of image, page needs optimmized image to reduce load time | Medium | Open | 1.Navigate to the login 2. Observe lack of image
UI002 | "Welcome Back" text appers incorrectly on logout panel | Low | Open | 1.Navigate to the logout panel top right corner 2.Observe the displayed message 3.Notice "welcome Back" text shown
FN003 | Emil address form lacks proper validation technique | Medium | Open | 1.Navigate to the Add user form 2.Enter an invalid email 3.Submit the form 4.Observe that no error is triggered
FN004 | Date fields not functioning correctly based on "filter by" not triggering the corresponding forms | High | Open | 1. Go to the dashboardpage 2.Select a value form 'filter by' dropdown 3. Observe the 'from date,' 'to date' which does not trigger or update result
FN005 | GIF file accepted as profile picture instead of static image | Medium | Open | 1.Navigate to the add user page 2.Click on "profile picture" 3.Select and upload a 'gif' file 4. Observe that the GIF is accepted
FN006 | Blood group field allows manual typing instead of dropdown selection | Medium | Open | 1. Navigate to the add user 2.Locate the blood group input field 3.Observe that the field allows free text entry 4. Enter a random or misspelled value
FN007 | password field lacks strength suggestion across multiple modules eg. Login page | High | Open | 1.Navigate to any module with a password field 2.Enter a weal password 3.Observe that no strength indicator or suggestion appers
UI008 | Eye icon for password preview duplicates during input type | High | Open | 1. Navigate to the login page 2. Click on the password field 3. Begin typing a password 4. Observe that the eye icon appears twice
UI009 | Inconsistent responsiveness across modules on various screen sizes | High | Open | 1. Access the application on different devices (desktop, tablet, mobile) 2. Navigate through multiple modules (e.g dashboard, profile, settings, forms) 3. Observe layout shifts overlapping elements or broken UI components
FN010 | Notification alert shows inappropriate or misleading time | High | Open | 1. Log in to the application 2. Open the notification panel 3. Observe timestamps on alerts